## 4. Update log book
Title: | Risk assessment for updating log books [4]
Date: | 25th January 2018
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1 | Computer will not start/cannot edit file | Cannot access log book file, therefore file may be lost and logbook cannot be accessed or updated | Medium | Need to keep backup online or elsewhere other than computer, so that log book can be accessed on another machine if needed. | Low | Medium | Medium
2 | Log book file corrupted/deleted | Cannot access log book file, therefore file may be lost and logbook cannot be accessed or updated | Medium | Need to keep regular backups on cloud storage or on a memory stick to avoid losing the whole file if lost or corrupted. | Low | Medium | Low
3 | Marker unable to access the document via OneDrive, Google Docs etc. | Cannot receive grades or feedback on the log book | Medium | Back up plan to send log book via email to marker if Docs/OneDrive is not working. Send this as a matter of priority if asked by marker. | Low | Medium | Low
4 | Late to submit log book | Cannot receive grades or feedback on the log book. Likely to fall behind. | Low | Ensure you complete the log book as you go (i.e. write about the day at the end of that day). | Low | Medium | Low
5 | Computer lost or stolen | Cannot access log book file, therefore file may be lost and logbook cannot be accessed or updated. Also will have lost university computer, consequences for that. | Low | Keep the log book backed up online or on a memory stick so that if the computer goes missing the log book is still accessible. Keep computer with you at all times, securely in given bag when not in use. | Low | Medium | Low

## Blank template
Title: | Risk assessment for
Date:
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1
2
3
4
5

## 5. Create work breakdown struc
Title: | Risk assessment for creating work breakdown structures [5]
Date: | 25th January 2018
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1 | Computer will not start/cannot edit file | Cannot access WBS file, therefore file may be lost and WBS cannot be accessed or updated | Medium | Need to keep backup online or elsewhere other than computer, so that WBS can be accessed on another machine if needed. | Low | Medium | Medium
2 | WBS file corrupted/deleted | Cannot access WBS file, therefore file may be lost and WBS cannot be accessed or updated | Medium | Need to keep regular backups on cloud storage or on a memory stick to avoid losing the whole file if lost or corrupted. | Low | Medium | Low
3 | Taking too long to complete WBS | May fall behind on other work, affects the timeline of the whole project. | Low | Refer to GANTT chart and stick to the timeframe we set. Have additional meetings outside of work hours if needed to complete the task on time. | Low | Medium | Low
4 | Forgotten necessary equipment: whiteboard pens, whiteboard eraser | Cannot write WBS on whiteboard as a team. | Low | Ensure we nominate someone to bring these items, keep the items next to the whiteboard in a pot. Keep spare pens also. | Low | Low | Low
5 | WBS rubbed off board | Our work on the board will be lost. Will need to spend time rewriting it - waste. | Medium | Take photographs of the board as we go along so if it is rubbed out we don’t lose any work. | Low | Medium | Medium
6 | WBS is incorrect/lacking in information | Poor WBS means we will have difficulty identifying tasks and therefore creating GANTT. This has knock on effect throughout project. | Medium | Check with PW, AO, IW that WBS is good, ask for improvements. Double check we have all information we need. | Low | Medium | Medium

## 6. Create group GANTT chart
Title: | Risk assessment for creating group GANTT chart [6]
Date: | 25th January 2018
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1 | Computer will not start/cannot edit file | Cannot access GANTT file, therefore file may be lost and GANTT cannot be accessed or updated | Medium | Need to keep backup online or elsewhere other than computer, so that GANTT can be accessed on another machine if needed. | Low | Medium | Medium
2 | Log book file corrupted/deleted | Cannot access GANTT file, therefore file may be lost and GANTT cannot be accessed or updated | Medium | Need to keep regular backups on cloud storage or on a memory stick to avoid losing the whole file if lost or corrupted. | Low | Medium | Low
3 | Taking too long to complete GANTT | May fall behind on other work, affects the timeline of the whole project. | Low | Have additional meetings outside of work hours if needed to complete the task on time. | Low | Medium | Low
4 | Forgotten necessary equipment/resources: computer, Microsoft Project, complete WBS | Cannot write GANTT | Low | Ensure we nominate someone to bring the computer. Check MS Project is installed on it. Ensure WBS is completed before we start GANTT. | Low | Low | Low
5 | GANTT is incorrect/lacking in information | Will struggle to work to the GANTT schedule if it is wrong. May find ourselves with too much work to do or too little. Possibility we will not get the project completed well and on time. | Medium | Check with PW, AO, IW that GANTT is good, ask for improvements. Double check we have all information we need. | Low | Medium | Medium
6 | Group unable to view group GANTT | Group will be unsure on where we are in terms of tasks, may not know what they are doing. Possibility we will not get the project completed well and on time. | Medium | Keep up-to-date A3 printout on our board at all times. Replace every time GANTT is updated and use version numbers. Also send latest copy of GANTT via email every time it is revised. | Low | Medium | Low

## 14. Obtain current SOPs
Title: | Risk assessment for obtaining current SOPs
Date: | 25th January 2017
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1
2
3
4
5

## 17. Visit manufacturing site to
Title: | Risk assessment for visiting manufacturing site to get information [17]
Date: | 2nd November 2017
Revision: | 1
Names: | Jack Farmer, Joshua Ramsay, Sofia Romera, Jay Brooker, Rohan Daddar, Oliver Slocombe
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1 | People do not have correct PPE (steel toe cap boots, goggles, high-vis jacket, ear plugs) | Unable to visit factory floor, would ve violating health and safety and risking personal safety. | High | Ensure we all pack appropriate PPE and check with each other that we are wearing it before we leave. Obtain ear plugs from inside entrance door. | Low | Medium | High
2 | Injury from forklift truck | Risk to own safety, serious injury possible | Low | Stick to H&S practises (wave at driver of forklift, stick to marked walkways where possible, look both ways before crossing) | Low | Low | Low
3 | Injury from machinery/equipment | Risk to own safety, serious injury possible | Low | Do not touch equipment as we are not trained, if we need to use it ask trained person. Keep long hair/lanyards/baggy clothes tucked away or tied up. Wear safety gloves if required (will be on sign next to machine). | Low | Low | Low
4 | Cannot find person we need/they are busy | Unable to find information we need potentially. | Medium | Contact person beforehand to try and set up a meeting and to check if they are available (email or phone call) | Low | Medium | Medium
5 | Cannot find information we need | Unable to complete task relating to the information as quickly. May need to come back another time. | Medium | Back up plan needed if we cannot find information (Accessible online? Paper documents on shop floor? Computer documents we can access?) | Low | High | Medium
6 | Unclear plan of what we will do when we visit | Unable to complete task May need to come back another time. May be wasting time doing something we do not need to do. | Medium | Create plan of why we are visiting, where specifically, who we are visiting, and questions we need to ask - before we leave. | Low | Medium | Medium
7 | Forgetting to bring any required equipment/resources | Unable to complete the tasks we went to do. | Medium | Create plan of what we will need, nominate somebody to ensure we bring all equipment/resources. | Low | High | Medium

## 19. Create spaghetti diagram
Title: | Risk assessment for creating a spaghetti diagram [19]
Date: | 25th January 2018
Revision: | 1
Names:
No. | Risk | Outcome | Risk Level | Solution | Achieved Risk Level | Influence | Probability
1 | Taking too long to complete diagram | May fall behind on other work, affects the timeline of the whole project. | Low | Have additional meetings outside of work hours if needed to complete the task on time. | Low | Medium | Low
2 | Forgotten necessary equipment/resources: computer, Microsoft Visio, A3 printer, string, tape measure, paper and pen | Cannot create diagram | Low | Ensure we nominate someone to bring the computer. Check MS Visio is installed on it. Bring tape measure, pen and paper to manufactruing site to make measurements of size of floor space and equipment. | Low | Low | Low
3 | Forgotten to take measurements of area | Cannot create full and to-scale diagram | Medium | Plan all measurements that need to be taken. Double check all measurements are present before leaving the manufacturing site. | Low | Medium | Medium
4 | Measurements taken inaccurate | Cannot create full and to-scale diagram | Medium | Take all measurements at least twice to ensure they are correct. Have two people using tape measure (one holding each end) and hold tape measure straight. | Low | Medium | Medium
5 | Computer will not start/cannot edit file | Cannot access Visio floor plan file, therefore file may be lost | Medium | Need to keep backup online or elsewhere other than computer, so that log book can be accessed on another machine if needed. | Low | Medium | Medium
6 | Visio file corrupted/deleted | Cannot access Visio floor plan file, therefore file may be lost | Medium | Need to keep regular backups on cloud storage or on a memory stick to avoid losing the whole file if lost or corrupted. | Low | Medium | Low
7 | Taking too long to complete spaghetti diagram | May fall behind on other work, affects the timeline of the whole project. | Low | Refer to GANTT chart and stick to the timeframe we set. Have additional meetings outside of work hours if needed to complete the task on time. | Low | Medium | Low
8 | Diagram is incorrect/lacking in information | Poor spaghetti diagram means we will have difficulty identifying waste (motion and transport) | Medium | Double check we have all information we need, think about possible imporvements as a group | Low | Medium | Medium